## Overview
DFP Network Project Plan Overview | Central European Media Enterprises
Client | CME
Main POCs | Martin Sedlak (CZ/SK) | sedlak@google.com
| Irina Fosa (RO) | irinafosa@google.com
| Balint Torok (BG) | btorok@google.com
Network Architecture
Country | Network ID | AdX ID
Romania | 36564804 | ca-pub-2589215577560035
Bulgaria | 120344282 | ca-pub-2330642468993824
Czech Republic | 27415282 | ca-pub-9203154443620784
Slovakia | 55080094 | ca-pub-3049867388240708
* Separate accounts for each entity
* Plan for workshops / in country trainings | agree dates / needs

## Business Requirement Gathering
Business Requirement Gathering |  |  | Romania - ProTV (example from earlier implementation) |  | CZ - TV Nova |  | MARKIZA-SLOVAKIA |  | BTV Media Group
Topic | Status | Question from Google | Answer from RO | Answer | Answer from (name) | Answer | Answer from (name) | Answer | Answer from (name) | Answer
General / Content Related |  | How many websites are you implementing? | Protv | We have 23 sites in our portfolio : 12 sites are ours and 11 operated. Most of them have mobile versions or are responsive. Also, apart from these, there are 19 microsites for all the important TV shows we host. Most important sites are: www.stirileprotv.ro, www.protv.ro, www.sport.ro
|  | How will you be selling inventory across your website properties? (individually, collectively, etc). | Protv | We will sell the inventory individually (each site) and collectively (more sites, all sites)
|  | Do you have any documentation that represents your current or intended site hierarchies? | Protv | No
|  | Development cycles - impact to timeline (ie: any upcoming launches or redesigns that could impact implementation timeline) | Protv | At the beginning of May we will launch the new design for www.stirileprotv.ro, our main news website
Page Layout |  | Describe your Page Layout(s). | Protv | We have 2 types of pages: pages with display banners only and pages with display banners and video instream ads
|  | Do you have a single or multiple page layouts on your network (E.g. One webpage with skyscraper/leaderboard, another webpage with skyscraper/bigbox, etc.)? | Protv | We have a multiple page layouts
|  | What ad sizes will you be using on your network? | Protv | 320x60,300x50,320x50 300x250, 300x600,728x90, 970x250, 980x60 Sticky, interstital,1000x120 branding
|  | Are ad sizes unique on any given page (E.g. only one 728x90 on a webpage)? | Protv | Most of the ad sizes are not unique (728x90 is the only ad size that is unique on some webpages)
Inventory Strategy |  | Could you describe your Inventory strategy/product offering ie. RON, ROS, Interstitial, Takeover, Other? | Protv | Most of our campaigns are impression based (standard display campaigns, ROC, RON, ROS, Interstital, Exclusive ad Takeover, special projects including widgets and contest pools) We also have some CPC and CPL campaigns
|  | Other ad products: Video, Games, Mobile | Protv | We have all video instream formats (preroll, midroll , postroll and overlayer - including POD's on some sites), outstream formats ( contextual video ads),mobile, mobile apps
|  | Could you describe your Targeting strategy including restrictions ie. User Registration Information Geotargeting, Computer System/Web Browser, Time/Day Based [Dayparting], Frequency Capped, Behavioral\Contextual targeting, Conflicting Content, Competing Advertisers, Premium Content, Premium Placement (above the fold/below the fold), Ad Hoc Restrictions based on Client Request, Other Custom Targeting? | Protv | We will use all described targeting offered by the ad server
|  | Could you describe your Creative Types ie. Standard Images (gifs, jpgs, png), Rich Media, Video, html, Third-Party Redirects (images, rich media, roadblocks, etc.)? | Protv | All types: images (images, rich media, interstitials, contextualscroll and contextual video ads, 3rd party HTML scripts), video, custom creatives and campaigns, 3rd party HTML scripts etc
DFP Users |  | Do you categorize your users in Teams / restricting inventory based on group/region? | Protv | Yes, we will categorize our users in teams or groups
Inventory Forecasting |  | Could you describe your Forecasting needs? | Protv | We need to forecast inventory targeted by country, sites, ad unit , placement, creative, days, hours, keywords, audience
Reporting |  | Could you describe how you generate reports? | Protv | There are several types of reports we use: for actual delivery ( 1) standard reports which should contain impressions clicks and unique users, (3) for forecast, for AdX performance. We run most of the reports on a daily basis, but there are also weekly and monthly
|  | Could you send us some sample reports? | Protv | Please find attached: 1) report by campaign 2) report by network 3) Daily inventory Forecast
Misc. Information |  | Using AdSense Backfill? | Protv | No
|  | Do you have any Third Party Integrations? | Protv | DSPs that already have AdX seats,DMP Audience, SSO proprietary system , AdUnity (through Bidswitch),Chartbeat, via API with Qlikview/Adverity
|  | Do you plan to have partners as part of your network whereby revenue sharing is needed? |  | Yes

## CZ - Project Plan
Task | Time | Completion Date | Link | Staff | Status | Initials
Call #1 - Project Kickoff | 1 hour |  |  | Sales Rep, Trafficker, DoubleClick
1. Getting Started | Week 1
1.1 Getting started guide | 1 day |  | goo.gl/MCiCn | Ad.ops | Not started
1.2 Product training |  |  | goo.gl/f876P | Trafficker | Not started
2. Contacting Support | Week 1
2.1 Customer Support Handbook | 30 mins |  | http://goo.gl/5YPHyv | Trafficker | Not started
3. Network Setup | Week 1
3.1 Sign in | 5 mins |  | goo.gl/BRYAv | Trafficker | Not started
3.2 Create users | 2 hours |  | goo.gl/yXZq6 | Trafficker | Not started
3.3 Create contacts | 2 hours |  | goo.gl/5lF69 | Trafficker | Not started
3.4 Create companies | 2 hours |  | goo.gl/rq6HE | Trafficker | Not started
4. Inventory Setup | Week 1
4.1 Identify your inventory | 1 day |  | goo.gl/0E1bg | Ad.ops, development, IT | Not started
4.2 Design your inventory | 1 day |  | http://goo.gl/DS5kkU | Ad.ops, development, IT | Not started
4.3 Build your inventory | 1 day |  | http://goo.gl/kpHSak | Ad.ops, development, IT | Not started
Call #2 - Inventory Review | 1 hour |  |  | Trafficker, Developer, DoubleClick
5. Trafficking Test | Week 2
5.1 Traffic test orders | 1 hour |  | goo.gl/m3LmR |  | Not started
5.2 Traffic test line items | 1 hour |  | goo.gl/Ua0a2 |  | Not started
5.3 Generate test ad tags | 1 hour |  | dfpgpt.appspot.com/ |  | Not started
6. Tagging Test | Week 2
6.1 Create test pages | 2 hours |  | dfpgpt.appspot.com/ |  | Not started
7. Migrate Campaigns | Week 2
7.1 Link AdSense/AdX to DFP | 30 mins |  | goo.gl/ZxWrDu |  | Not started
7.2 Read up on priorities | 30 mins |  | goo.gl/rJkQE |  | Not started
7.3 Read up on creatives | 30 mins |  | http://goo.gl/9D1w4I |  | Not started
7.4 Read up on macros | 30 mins |  | goo.gl/Smh5j |  | Not started
7.5 Create custom templates | 2 days |  |  |  | Not started
Call #3 - Ad Tags & Reporting | 1 hour |  |  | Trafficker, Developer, DoubleClick
7. Migrate Campaigns (cont'd) | Week 3
7.5 IMA SDK | 4 hours |  | goo.gl/V4yxd |  | Not started
7.6 Traffic all campaigns | 3 days |  | goo.gl/m3LmR |  | Not started
8. Tag Your Site | Week 3
8.1 Read up on GPT | 1 day |  | goo.gl/hCycc |  | Not started
8.2 Configure CMS | 2 days |  | goo.gl/xE1rB |  | Not started
8.3 Tag Your Site | 2 days |  | goo.gl/xE1rB |  | Not started
9. Optimize Your Site | Week 3
9.1 Optimize your page loading times | Optional |  | goo.gl/OMyzc |  | Not started
9.2 Optimize your social experience | Optional |  | goo.gl/A2Ljv |  | Not started
Call #4 - Go Live & Beyond | 1 hour |  |  | Trafficker, Developer, DoubleClick
10. Monitor Delivery | Week 4
10.1 Create saved reports | 1 day |  | goo.gl/Hhs6Y |  | Not started
10.2 Read up on delivery | 1 day |  | goo.gl/3xgpGC |  | Not started
10.3 Read up on forecasting | 1 day |  | goo.gl/HIz6K |  | Not started
11. Go Live
11.1 Go live with ad tags | 1 day |  |  |  | Not started
11.2. Transition to support | 1 day |  |  |  | Not started
12. Video/Mobile Features | (Optional)
12.1 Getting started with video | 4 hours |  | goo.gl/XGdhKY |  | Not started
12.2 Getting started with mobile | 4 hours |  | goo.gl/ZDsN6A |  | Not started
13. Developer Resources | (Optional)
13.1 DFP API | 4 hours |  | goo.gl/mqlTp |  | Not started
Call #5 - Getting Started with Video | TBC
14.1 Read video guide | 2 hours |  | goo.gl/u9MfN | Trafficker | Not started
14.2 Create video ad units | 10 mins |  | goo.gl/JeAF1 | Trafficker | Not started
14.3 Generate video ad tags | 10 mins |  | goo.gl/Miep7 | Trafficker, Developer | Not started
14.4 Add key-values to tags | 1 hour |  | goo.gl/oMjRC | Trafficker, Developer | Not started
14.5 Create a video line item | 20 mins |  | goo.gl/UbZAZ | Trafficker | Not started
14.6 Create a video creative set | 20 mins |  | goo.gl/qP3id | Trafficker | Not started
14.7 Review video creative reporting | 20 mins |  | goo.gl/WVwpr | Trafficker | Not started

## SK - Project Plan
Task | Time | Completion Date | Link | Staff | Status | Initials
Call #1 - Project Kickoff | 1 hour |  |  | Sales Rep, Trafficker, DoubleClick
1. Getting Started | Week 1
1.1 Getting started guide | 1 day |  | goo.gl/MCiCn | Ad.ops | Not started
1.2 Product training |  |  | goo.gl/f876P | Trafficker | Not started
2. Contacting Support | Week 1
2.1 Customer Support Handbook | 30 mins |  | http://goo.gl/5YPHyv | Trafficker | Not started
3. Network Setup | Week 1
3.1 Sign in | 5 mins |  | goo.gl/BRYAv | Trafficker | Not started
3.2 Create users | 2 hours |  | goo.gl/yXZq6 | Trafficker | Not started
3.3 Create contacts | 2 hours |  | goo.gl/5lF69 | Trafficker | Not started
3.4 Create companies | 2 hours |  | goo.gl/rq6HE | Trafficker | Not started
4. Inventory Setup | Week 1
4.1 Identify your inventory | 1 day |  | goo.gl/0E1bg | Ad.ops, development, IT | Not started
4.2 Design your inventory | 1 day |  | http://goo.gl/DS5kkU | Ad.ops, development, IT | Not started
4.3 Build your inventory | 1 day |  | http://goo.gl/kpHSak | Ad.ops, development, IT | Not started
Call #2 - Inventory Review | 1 hour |  |  | Trafficker, Developer, DoubleClick
5. Trafficking Test | Week 2
5.1 Traffic test orders | 1 hour |  | goo.gl/m3LmR |  | Not started
5.2 Traffic test line items | 1 hour |  | goo.gl/Ua0a2 |  | Not started
5.3 Generate test ad tags | 1 hour |  | dfpgpt.appspot.com/ |  | Not started
6. Tagging Test | Week 2
6.1 Create test pages | 2 hours |  | dfpgpt.appspot.com/ |  | Not started
7. Migrate Campaigns | Week 2
7.1 Link AdSense/AdX to DFP | 30 mins |  | goo.gl/ZxWrDu |  | Not started
7.2 Read up on priorities | 30 mins |  | goo.gl/rJkQE |  | Not started
7.3 Read up on creatives | 30 mins |  | http://goo.gl/9D1w4I |  | Not started
7.4 Read up on macros | 30 mins |  | goo.gl/Smh5j |  | Not started
7.5 Create custom templates | 2 days |  |  |  | Not started
Call #3 - Ad Tags & Reporting | 1 hour |  |  | Trafficker, Developer, DoubleClick
7. Migrate Campaigns (cont'd) | Week 3
7.5 IMA SDK | 4 hours |  | goo.gl/V4yxd |  | Not started
7.6 Traffic all campaigns | 3 days |  | goo.gl/m3LmR |  | Not started
8. Tag Your Site | Week 3
8.1 Read up on GPT | 1 day |  | goo.gl/hCycc |  | Not started
8.2 Configure CMS | 2 days |  | goo.gl/xE1rB |  | Not started
8.3 Tag Your Site | 2 days |  | goo.gl/xE1rB |  | Not started
9. Optimize Your Site | Week 3
9.1 Optimize your page loading times | Optional |  | goo.gl/OMyzc |  | Not started
9.2 Optimize your social experience | Optional |  | goo.gl/A2Ljv |  | Not started
Call #4 - Go Live & Beyond | 1 hour |  |  | Trafficker, Developer, DoubleClick
10. Monitor Delivery | Week 4
10.1 Create saved reports | 1 day |  | goo.gl/Hhs6Y |  | Not started
10.2 Read up on delivery | 1 day |  | goo.gl/3xgpGC |  | Not started
10.3 Read up on forecasting | 1 day |  | goo.gl/HIz6K |  | Not started
11. Go Live
11.1 Go live with ad tags | 1 day |  |  |  | Not started
11.2. Transition to support | 1 day |  |  |  | Not started
12. Video/Mobile Features | (Optional)
12.1 Getting started with video | 4 hours |  | goo.gl/XGdhKY |  | Not started
12.2 Getting started with mobile | 4 hours |  | goo.gl/ZDsN6A |  | Not started
13. Developer Resources | (Optional)
13.1 DFP API | 4 hours |  | goo.gl/mqlTp |  | Not started
Call #5 - Getting Started with Video | TBC
14.1 Read video guide | 2 hours |  | goo.gl/u9MfN | Trafficker | Not started
14.2 Create video ad units | 10 mins |  | goo.gl/JeAF1 | Trafficker | Not started
14.3 Generate video ad tags | 10 mins |  | goo.gl/Miep7 | Trafficker, Developer | Not started
14.4 Add key-values to tags | 1 hour |  | goo.gl/oMjRC | Trafficker, Developer | Not started
14.5 Create a video line item | 20 mins |  | goo.gl/UbZAZ | Trafficker | Not started
14.6 Create a video creative set | 20 mins |  | goo.gl/qP3id | Trafficker | Not started
14.7 Review video creative reporting | 20 mins |  | goo.gl/WVwpr | Trafficker | Not started

## BG - Project Plan
Task | Time | Completion Date | Link | Staff | Status | Initials
Call #1 - Project Kickoff | 1 hour |  |  | Sales Rep, Trafficker, DoubleClick
1. Getting Started | Week 1
1.1 Getting started guide | 1 day |  | goo.gl/MCiCn | Ad.ops | Not started
1.2 Product training |  |  | goo.gl/f876P | Trafficker | Not started
2. Contacting Support | Week 1
2.1 Customer Support Handbook | 30 mins |  | http://goo.gl/5YPHyv | Trafficker | Not started
3. Network Setup | Week 1
3.1 Sign in | 5 mins |  | goo.gl/BRYAv | Trafficker | Not started
3.2 Create users | 2 hours |  | goo.gl/yXZq6 | Trafficker | Not started
3.3 Create contacts | 2 hours |  | goo.gl/5lF69 | Trafficker | Not started
3.4 Create companies | 2 hours |  | goo.gl/rq6HE | Trafficker | Not started
4. Inventory Setup | Week 1
4.1 Identify your inventory | 1 day |  | goo.gl/0E1bg | Ad.ops, development, IT | Not started
4.2 Design your inventory | 1 day |  | http://goo.gl/DS5kkU | Ad.ops, development, IT | Not started
4.3 Build your inventory | 1 day |  | http://goo.gl/kpHSak | Ad.ops, development, IT | Not started
Call #2 - Inventory Review | 1 hour |  |  | Trafficker, Developer, DoubleClick
5. Trafficking Test | Week 2
5.1 Traffic test orders | 1 hour |  | goo.gl/m3LmR |  | Not started
5.2 Traffic test line items | 1 hour |  | goo.gl/Ua0a2 |  | Not started
5.3 Generate test ad tags | 1 hour |  | dfpgpt.appspot.com/ |  | Not started
6. Tagging Test | Week 2
6.1 Create test pages | 2 hours |  | dfpgpt.appspot.com/ |  | Not started
7. Migrate Campaigns | Week 2
7.1 Link AdSense/AdX to DFP | 30 mins |  | goo.gl/ZxWrDu |  | Not started
7.2 Read up on priorities | 30 mins |  | goo.gl/rJkQE |  | Not started
7.3 Read up on creatives | 30 mins |  | http://goo.gl/9D1w4I |  | Not started
7.4 Read up on macros | 30 mins |  | goo.gl/Smh5j |  | Not started
7.5 Create custom templates | 2 days |  |  |  | Not started
Call #3 - Ad Tags & Reporting | 1 hour |  |  | Trafficker, Developer, DoubleClick
7. Migrate Campaigns (cont'd) | Week 3
7.5 IMA SDK | 4 hours |  | goo.gl/V4yxd |  | Not started
7.6 Traffic all campaigns | 3 days |  | goo.gl/m3LmR |  | Not started
8. Tag Your Site | Week 3
8.1 Read up on GPT | 1 day |  | goo.gl/hCycc |  | Not started
8.2 Configure CMS | 2 days |  | goo.gl/xE1rB |  | Not started
8.3 Tag Your Site | 2 days |  | goo.gl/xE1rB |  | Not started
9. Optimize Your Site | Week 3
9.1 Optimize your page loading times | Optional |  | goo.gl/OMyzc |  | Not started
9.2 Optimize your social experience | Optional |  | goo.gl/A2Ljv |  | Not started
Call #4 - Go Live & Beyond | 1 hour |  |  | Trafficker, Developer, DoubleClick
10. Monitor Delivery | Week 4
10.1 Create saved reports | 1 day |  | goo.gl/Hhs6Y |  | Not started
10.2 Read up on delivery | 1 day |  | goo.gl/3xgpGC |  | Not started
10.3 Read up on forecasting | 1 day |  | goo.gl/HIz6K |  | Not started
11. Go Live
11.1 Go live with ad tags | 1 day |  |  |  | Not started
11.2. Transition to support | 1 day |  |  |  | Not started
12. Video/Mobile Features | (Optional)
12.1 Getting started with video | 4 hours |  | goo.gl/XGdhKY |  | Not started
12.2 Getting started with mobile | 4 hours |  | goo.gl/ZDsN6A |  | Not started
13. Developer Resources | (Optional)
13.1 DFP API | 4 hours |  | goo.gl/mqlTp |  | Not started
Call #5 - Getting Started with Video | TBC
14.1 Read video guide | 2 hours |  | goo.gl/u9MfN | Trafficker | Not started
14.2 Create video ad units | 10 mins |  | goo.gl/JeAF1 | Trafficker | Not started
14.3 Generate video ad tags | 10 mins |  | goo.gl/Miep7 | Trafficker, Developer | Not started
14.4 Add key-values to tags | 1 hour |  | goo.gl/oMjRC | Trafficker, Developer | Not started
14.5 Create a video line item | 20 mins |  | goo.gl/UbZAZ | Trafficker | Not started
14.6 Create a video creative set | 20 mins |  | goo.gl/qP3id | Trafficker | Not started
14.7 Review video creative reporting | 20 mins |  | goo.gl/WVwpr | Trafficker | Not started

## Training participants
CZ:
Hanischová | Lucie | Lucie.Hanischova@nova.cz
Sheiko | Luiza | Luiza.Sheiko@nova.cz
Kovář | Luboš | Lubos.Kovar@novatv.cz
Mikeš | Jakub | Jakub.Mikes@nova.cz
Michal | Malencik | Michal.Malencik@cme.net
Lukas | Kubat | Lukas.Kubat@cme.net
Starek, | Michal | Michal.Starek@cme.net
RO:
Mihaela | Vladau | mihaela.vladau@protv.ro
Irina | Desliu | irina.desliu@protv.ro
Mircea | Serdin | Mircea.serdin@protv.ro
Silviu | Bobicescu | Silviu.bobicescu@protv.ro
Alma | Ghizdavescu-Iosip | alma.iosip@protv.ro
Ana Elena | Ion | ana.ion@protv.ro
Corina | Petrea | corina.petrea@protv.ro
Andreea | Ivanciu | andreea.ivanciu@protv.ro
Andrei | Carciumaru | andrei.carciumaru@protv.ro
Narcisa | Badea | narcisa.badea@protv.ro
Maria | Muntianu | maria.muntianu@protv.ro
Hanaan | Yaseen | Hanaan.yaseen@protv.ro
SK:
Brtan | Martin | Brtan.Martin@markiza.sk
BG
Alexander | Boytchev | alexander_boytchev@btv.bg
Irena | Vasileva
Jasmina | Gevezieva
Ivan | Hidzhov
Atoan | Valchev

## Questions
Date | Status | Questions from | Answers/comments from Google | Notes

## Example of Inventory Design
Note: Usage of more than 2 levels of ad units requires the Google Publisher Tag (GPT) to be used. Refer to the Help Center for more information and tagging examples.
GPT Tagging: | https://www.google.com/support/dfp_premium/bin/topic.py?hl=en&topic=28788
Name Level 1 | Name Level 2 | Name Level 3 | Name Level 4 | Name Level 5 | Ad Unit Sizes | Ad Unit Status | Target Window | Ad Unit Description | Is Special Ad Unit
SiteSport.com | [5 empty] | ACTIVE | TOP |  | FALSE
SiteSport.com | Football |  |  |  |  | ACTIVE | TOP |  | FALSE
SiteSport.com | Football |  |  |  |  | ACTIVE | TOP |  | FALSE
SiteSport.com | Football |  |  |  |  | ACTIVE | TOP |  | FALSE
SiteSport.com | Sports | Golf |  |  |  | ACTIVE | TOP |  | FALSE
SiteSport.com | Sports | Box |  |  |  | ACTIVE | TOP |  | FALSE
SiteSport.com | Sports | Basketball |  |  |  | ACTIVE | TOP |  | FALSE
SiteSport.com | Other |  |  |  |  | ACTIVE | TOP |  | FALSE
SiteSport.com | Other | Video |  |  | 400x300v (728x90) | ACTIVE | TOP |  | FALSE
SiteSport.com | Other | Updates |  |  |  | ACTIVE | TOP |  | FALSE
SiteNews.com | International |  |  |  |  | ACTIVE | TOP |  | FALSE
SiteNews.com | International |  |  |  | 160x600, 300x250, 728x90 | ACTIVE | TOP |  | FALSE
SiteNews.com | Social |  |  |  | 160x600, 300x250, 728x90 | ACTIVE | TOP |  | FALSE
SiteNews.com | Politic | Article |  |  |  | ACTIVE | TOP |  | FALSE
SiteNews.com | Politic | Article | Wide Skyscraper |  | 160x600 | ACTIVE | TOP |  | FALSE
SiteNews.com | Politic | Article | Leaderboard | Top | 728x90 | ACTIVE | TOP |  | FALSE

## Network Design Summary
DFP Network Design Document Summary
Network Architecture
Network Name | NETWORK NAME
Network ID | NETWORK ID
Client Targeting Object Usage
Ad Unit Level 1 | Ad Unit Level 1 will be used to target each website which ProTV maintains (e.g. stirileprotv.ro, sport.ro). This should include separate ad units for mobile apps.
Ad Unit Level 2 | Ad Unit Level 2 will be used to target each at least one section of the top level ad unit. This should include a separate ad unit for the site front page
Ad Unit Level 3 | Ad Unit Level 3 will be used to target each at least one sub-section of the sections on ad unit level 2. This includes a separate level-3 ad unit for the front page of each section in level 2, where such pages exist.
Ad Unit Level 4 | Ad Unit Level 4 can be used to target each at least one sub-sub-section of your pages. Same instructions as level 3. If no sub-sub-sections exist, then use the instructions for level 5
Ad Unit Level 5 | The highest ad unit level should be used to create ad units for each position in the pages for that particular section/subsection. For example, for the ad unit 'Site' -> 'Section A' -> Frontpage, you should have ad units on the last level with names such as 'top_banner', 'right_skyscraper', 'left_mpu' or similar names corresponding to the ad positions of the front page of "Section A" on your site.
Placements | Placements can be used to group together Ad Units that are commonly sold as packages, but are not part of the same hierarchy, such as Sports sections across your sites.
Custom Targeting Usage | Custom Targeting will be used to target more granular content in addition to parameters such as demographic specific information (age and gender).
Notes
Notes on limits: - Ad unit names can be up to 100 characters in length. Don't use spaces or special characters - only letters, numbers, underscores, and dashes are recommended. - Neither key-values or ad units are case-sensitive. - Each key or value can contain up to 252 characters - No hard limit on the number key-values a line item can be targeted to - Limit to the number of key-value characters you can include in an ad tag is 2,000 - Internet Explorer URL length limit is 2,083 - The maximum number of boolean AND relationships per line item is 8 (so you can have 7 ANDs) - Limit to # key-value characters for forecasting purposes: 1000
Notes on defaults: - Default max number of reportable key-values per network is 50,000 (e.g. 1 key with 50,000 values would reach the limit, or 100 keys with 500 values would reach the limit) - Default max number of keys is 20 - Default max number of values per key is 200

## General targeting
General targeting
Use this tab to decide what's the best way to target a portion of your inventory
Targeting type | Description | Sample | Targeting type | Notes
Position | Targeting different ad slots on the page, e.g. the top 300x250 from the 300x250 below the fold | pos=top | Custom targeting | Why? Position will exist on every page in your network, so it's much easier to create one key-value than many "top" and "bottom" ad units for every ad unit in your network.
Mobile devices | iPhones, iPads, Android devices | iPhone 5S | DFP-provided | Why? DFP already figures this out, so you don't need to pass it to DFP
Sections | Topic sections of website | Opinion section | Ad unit | Why? Many pages are likely grouped in the Opinion section, but you may sell ads against the whole section, so it's convenient to have that grouped together in a single bundle/unit
All the homepages | Homepages from each topic section across the site | Homepages | Placement | Why? With a standard hierarchy, many sections and subsections will have their own homepage ad units (like /Opinion/Homepage and /Sports/Homepage and /World/Homepage). Even so, you can create custom groupings with the Placements inventory type.
NOTES
- Use this tab to input all of the targeting that you plan to use in your DFP network. Anything that you sell against is worth considering here.
- Avoid using special characters outside of numbers, letters, dashes, or underscores. To account for spaces, you have the additional option of using + or %20 in the ad tag, but the trafficker will not have to enter these in the UI - they can just enter a space.

## Inventory Design
Note: Usage of more than 2 levels of ad units requires the Google Publisher Tag (GPT) to be used. Refer to the Help Center for more information and tagging examples.
GPT Tagging: | https://www.google.com/support/dfp_premium/bin/topic.py?hl=en&topic=28788
Ad Unit 1 | Ad Unit 2 | Ad Unit 3 | Ad Unit 4 | Ad Unit 5 | Size(s)
sample
sportssite.com | sports | handball | leaderboard |  | sz=728x90

## Custom Targeting Values
Custom Targeting Values
Granular Content Targeting
Display Name | Name | Value Type | Values | Example | Notes
Sample
Position | pos | predefined | top, right_top, right_bottom, bottom | pos=top | Useful to make it easier to target similar-named positions across different sections.
NOTES
- With the exception of reserved custom targeting values, the key and value naming convention is up to [CLIENT NAME].
- Avoid using special characters outside of numbers, letters, dashes, or underscores. To account for spaces, you have the additional option of using + or %20 in the ad tag, but the trafficker will not have to enter these in the UI - they can just enter a space.